NexaCare Solutions: Testing and Release Planning Kit

Prepared by: Systems Professional (NexaCare Solutions)
 Role: Systems Analyst
 Project: Appointment Scheduling Platform – Version 3.0 Release
 Date: October 19, 2026

Project scenario

NexaCare Solutions is a healthcare technology company supporting over 300 clinics across North America. The organization is preparing to launch Version 3.0 of its web-based appointment scheduling platform.

This version introduces new features that aim to improve usability, patient engagement, and clinic operations. As the Systems Analyst, your responsibility is to coordinate and document a complete testing and release plan to ensure a safe, compliant, and successful rollout.

Key features in version 3.0

- SMS reminders

- Real-time doctor availability

- Calendar integration with Google and Outlook

- Redesigned user interface

Key considerations

- HIPAA compliance (over 1.2M patient records)

- First-time integration with third-party SMS provider

- Diverse client configurations (from basic to API-integrated systems)

- Pilot program for 20 clinics prior to full release

- Scheduled deployment window: Saturday, 12:00 AM – 6:00 AM EST

Test strategy outline

Overall approach

Our test strategy adopts a comprehensive, risk-based, and compliance-first methodology tailored specifically to NexaCare v3.0. Following a past data loss incident in another product line, leadership mandates zero-data-loss and rigorous regression protection. Testing is structured across 4 distinct operational tiers:
1. Component & Unit Testing: Input normalization, slot state machines, deterministic phone number parsing (E.164).
2. Multi-System Integration Testing: External contracts with the newly integrated third-party SMS gateway, bi-directional Google/Outlook Calendar OAuth webhooks, and legacy clinic PMS REST APIs.
3. Concurrency & Performance Testing: Simulating 500 baseline up to 2,500 concurrent virtual users during peak Monday morning surges (3-5x normal traffic) to prevent deadlocks and race conditions.
4. User Acceptance Testing (UAT) & Pilot Validation: Staged rollout starting with 20 pre-selected pilot clinics of diverse technical maturity (basic standalone web portal vs. deep EHR/PMS API integrations) to validate real operational workflows before full cutover to 300+ clinics.

Types of testing and rationale

| Type of Testing | Purpose / Rationale |
| --- | --- |
| Unit & Component Testing | Validates isolated business logic, input sanitization, phone number formatting (E.164), and appointment slot state machines before integration. |
| Integration Testing | Verifies contracts with external third-party SMS provider, Google/Outlook Calendar OAuth 2.0 endpoints, and clinic PMS REST APIs. |
| System & Regression Testing | Ensures end-to-end booking flows operate flawlessly and verifies that legacy functionality across 300 clinics remains intact. |
| Security & Compliance Testing | Audits HIPAA PHI handling, TLS 1.3 transit encryption, AES-256 rest encryption, and role-based access control (RBAC). |
| Performance & Stress Testing | Simulates Monday morning surge (1,500-2,500 concurrent users) to prove sub-3s response time and zero deadlocks. |
| User Acceptance Testing (UAT) | Conducted with 20 pre-selected pilot clinics with varying technical maturity to validate operational clinic workflows. |

Feature test priorities

- P0 (Critical/Blocker): Data migration schema validation (1.2M records), ACID booking transactions, real-time doctor availability concurrency locks (double-booking prevention), HIPAA PHI encryption at rest/in transit, and clinic PMS API backward compatibility.
- P1 (High): Automated SMS reminder engine (T-24h/T-1h dispatch via new third-party gateway), bi-directional Google/Outlook Calendar synchronization, rate limiting & retry queues.
- P2 (Medium): Redesigned responsive UI across mobile/desktop, WCAG 2.1 AA screen reader & color contrast compliance, pilot clinic telemetry tracking.
- P3 (Low): Micro-animations and minor static text updates.

Testing objectives

1. Data Integrity & HIPAA Compliance: Ensure zero data corruption across 1.2M+ patient records with AES-256 rest encryption and TLS 1.3 transit encryption.
2. High Concurrency & Scalability: Guarantee sub-3-second booking completion under 2,500 concurrent sessions during peak Monday 8-10 AM windows.
3. Interoperability & Reliability: Validate error-free integration with external SMS gateway, OAuth calendar providers, and PMS APIs with automated circuit breakers.
4. Usability & Accessibility: Meet WCAG 2.1 AA standards for seamless clinic staff and patient booking workflows across desktop, tablet, and mobile browsers.

Tools and frameworks

- Functional & Regression Automation: Cypress, Playwright, Jest, JUnit 5, Mockito.
- API & Integration Testing: Postman, Newman, REST-assured, WireMock (for SMS & Calendar OAuth mocking).
- Performance & Load Testing: Apache JMeter, k6 (simulating 500 to 2,500 concurrent virtual users).
- Security & Static Analysis: OWASP ZAP, SonarQube, Snyk (HIPAA & SAST/DAST scanning).
- Test Environments: Staging / Pre-Production mirror environment populated with anonymized, HIPAA-compliant dataset.

Traceability matrix

| Requirement ID | Requirement Description | Test Case ID(s) | Coverage Status | Priority / Risk |
| --- | --- | --- | --- | --- |
| REQ-01 | Automated SMS reminders dispatched 24h & 1h prior to appointment via 3rd party | TC-SMS-01, TC-SMS-02 | Covered (Standard & Edge) | P1 - High |
| REQ-01-A | SMS opt-out (STOP) compliance handling under TCPA/HIPAA regulations | TC-SMS-03 | Covered (Compliance) | P0 - Critical |
| REQ-01-B | SMS delivery retry on carrier throttling or rate-limiting (429 Too Many Requests) | TC-SMS-04 (Edge) | Covered (Edge) | P1 - High |
| REQ-02 | Real-time doctor availability broadcast across active clinic browser sessions | TC-AVAIL-01 | Covered (Standard) | P0 - Critical |
| REQ-02-A | Concurrent appointment booking race condition & double-booking prevention | TC-AVAIL-02 (Edge) | Covered (Edge) | P0 - Critical |
| REQ-02-B | Doctor availability update under spotty clinic Wi-Fi & WebSocket disconnect | TC-AVAIL-03 (Edge) | Covered (Pilot Clinic & Edge) | P1 - High |
| REQ-03 | Bi-directional Google Calendar and Microsoft Outlook event synchronization | TC-CAL-01, TC-CAL-02 | Covered (Standard) | P1 - High |
| REQ-03-A | Calendar sync handling when patient revokes OAuth permission or token expires | TC-CAL-03 (Edge) | Covered (Edge) | P1 - High |
| REQ-03-B | Calendar event synchronization across mismatched clinic and patient timezones | TC-CAL-04 (Edge) | Covered (Edge) | P1 - High |
| REQ-04 | Redesigned UI responsiveness across Mobile (375px), Tablet, and Desktop (1440px) | TC-UI-01, TC-UI-02 | Covered (Mobile/Desktop) | P2 - Medium |
| REQ-04-A | Redesigned UI WCAG 2.1 AA accessibility (screen reader & keyboard tab navigation) | TC-UI-03 | Covered (Accessibility) | P2 - Medium |
| REQ-05 | Backward compatibility for third-party clinic PMS REST API integrations | TC-API-01, TC-API-02 | Covered (API/UI & Pilot) | P0 - Critical |
| REQ-05-A | Pilot clinic validation: Hybrid workflow (Clinic PMS API write + Web Portal view) | TC-PILOT-01 | Covered (Pilot Clinic) | P0 - Critical |
| REQ-06 | Data migration schema transformation & record reconciliation (1.2M records) | TC-MIG-01, TC-MIG-02 | Covered (Data Integrity) | P0 - Critical |
| REQ-07 | Monday morning peak load concurrency handling (2,500 concurrent users, 3-5x normal) | TC-PERF-01 | Covered (Performance) | P0 - Critical |

Annotated test plans

Feature 1: Automated SMS Reminder Engine (Third-Party Gateway Integration)

Test Objective: Validate timely, compliant, and reliable dispatch of automated SMS reminders at T-24h and T-1h intervals via the newly integrated third-party SMS provider, with resilient error, throttling, and opt-out handling.

Preconditions: Patient account configured with valid mobile phone number; appointment scheduled >24 hours ahead; Third-party SMS sandbox and webhook endpoints active; HIPAA consent flag set to OPTED_IN.

Test cases

| Step | Test Action | Expected Result | Risks / Notes |
| --- | --- | --- | --- |
| TC-SMS-01.1 | Trigger automated cron scheduler to query appointments due for T-24h and T-1h reminder notifications. | Query retrieves eligible appointments without database table locks; dispatches queue message. | Edge Case: Timezone calculation discrepancies between clinic local time (e.g. EST) and UTC database timestamps. |
| TC-SMS-01.2 | Generate SMS message payload without diagnostic or physician specialty PHI (HIPAA Minimum Necessary Rule). | Payload contains only clinic name, appointment date/time, and opt-out instruction (e.g. 'Reply STOP to cancel'). | Risk: Regulatory HIPAA violation and legal penalty if medical specialty or diagnosis is transmitted in plain text SMS. |
| TC-SMS-01.3 | Dispatch payload via REST API to third-party SMS gateway with mock carrier network. | HTTP 200 OK received; message ID stored; status updated to SENT within <= 2 minutes of scheduled dispatch. | Risk: Third-party API rate limiting (429 Too Many Requests). Must implement token-bucket throttling and exponential backoff. |
| TC-SMS-01.4 | Simulate incoming SMS webhook with 'STOP' response from patient (TCPA Opt-Out). | Database immediately updates patient preference to OPTED_OUT; audit log recorded; zero future SMS sent. | Compliance: Mandatory TCPA mandate. Immediate suppression of all automated messaging across the platform. |

Deployment checklist

Pre-deployment tasks

| Task Description | Owner / Team | Est. Time | Dependencies / Notes |
| --- | --- | --- | --- |
| Final code freeze across all v3.0 release branches & artifact tagging | DevOps Lead | T-48h | Signed Docker images published to secure registry |
| Broadcast deployment advisory to all 300+ clinics detailing 6h window | Support Lead | T-24h | Email and in-app banner notifications sent |
| Execute Staging environment migration rehearsal dry run (1.2M records) | DBA / QA Lead | T-12h | 100% row count and checksum match achieved |
| Verify production backup storage capacity and failover availability | DevOps / SRE | T-2h | Secondary S3 replication and snapshot scripts verified |

Deployment window tasks

| Task Description | Owner / Team | Time Window | Prerequisites |
| --- | --- | --- | --- |
| Enable global maintenance mode and sever incoming web traffic | DevOps Lead | 12:00 AM - 12:15 AM | Load balancer routing updated to static maintenance splash |
| Execute cold full snapshot of 1.2M patient production database | Lead DBA | 12:15 AM - 01:00 AM | Gate 1: Verified snapshot taken and cryptographically hashed |
| Execute DDL schema transformations & batch data migration | Lead DBA | 01:00 AM - 02:30 AM | Batch chunks of 10,000 rows; zero unhandled exceptions |
| Run post-migration reconciliation script (100% row match) | Lead DBA / QA | 02:30 AM - 03:00 AM | Gate 2: Target row count = 1,200,000; checksum verified |
| Deploy v3.0 backend services & frontend static assets | DevOps Lead | 03:00 AM - 03:30 AM | Kubernetes pods reach READY status; secrets mounted |
| Execute production smoke test suite & live SMS/Calendar verification | QA Lead | 03:30 AM - 04:30 AM | 100% core test cases pass; sub-3s booking confirmed |
| Formal Go/No-Go Decision Meeting with all Leads | Release Manager | 04:30 AM - 04:45 AM | Gate 3: Hard deadline. Decision to cutover or rollback |
| Cutover access for 20 Pilot Clinics; monitor initial telemetry | DevOps / Support | 04:45 AM - 05:30 AM | Pilot clinics operational; zero P0/P1 tickets logged |
| Full public cutover for remaining 280+ clinics; lift maintenance | Release Manager | 05:30 AM - 06:00 AM | Platform fully operational across North America |

Post-deployment tasks

| Task Description | Owner / Team | Est. Time | Dependencies / Notes |
| --- | --- | --- | --- |
| Establish 48-Hour Virtual War Room for Hypercare monitoring | SRE / DevOps | 06:00 AM onwards | Cross-functional team on active bridge |
| Monitor real-time Golden Signals (Latency, Traffic, Errors, Saturation) | DevOps / SRE | Continuous | Datadog / Prometheus dashboards streaming live metrics |
| Triage pilot clinic feedback and direct support escalation queue | Support Lead | Hourly checks | Priority SLA < 15 minutes for 20 pilot clinics |
| Deliver daily executive operational health summaries to leadership | Systems Lead | Daily 05:00 PM | Comprehensive telemetry, error counts, and ticket analysis |

Go / No-Go criteria

- 1. Technical Go Conditions: 100% schema migration match (1.2M records); zero P0/P1 defects in smoke tests; API P95 latency < 500ms; external SMS/Calendar webhooks returning HTTP 200.
2. Operational Go Conditions: DevOps, DBA, and QA leads provide unanimous written sign-off by 04:30 AM EST.
3. Hard No-Go Triggers: Any data loss/corruption; smoke test failure rate > 5%; unresolvable DB deadlocks; or clock reaching 04:30 AM EST without QA sign-off (mandating immediate rollback to preserve 6:00 AM opening).

Rollback strategy

Conditions that trigger rollback

1. Data corruption, truncation, or reconciliation mismatch > 0.01% of patient records.
2. Migration or critical smoke test incomplete by 04:30 AM EST hard deadline.
3. Core appointment booking engine failure, persistent double-booking, or security vulnerability.
4. Database connection pool exhaustion (>95%) or sustained 5xx error rate > 2%.

Rollback procedure

| Step | Description | Responsible Team / Person |
| --- | --- | --- |
| Step 1 | Enforce global maintenance mode and isolate database connections | DevOps Lead |
| Step 2 | Scale down all v3.0 application containers and background workers to 0 | DevOps Lead |
| Step 3 | Drop working database and restore from 12:15 AM verified pre-deployment snapshot | Lead DBA |
| Step 4 | Execute verification script confirming 1,200,000 legacy records intact | Lead DBA / QA |
| Step 5 | Redeploy stable v2.x container images and revert DNS/ingress routing rules | DevOps Lead |
| Step 6 | Execute v2.x sanity smoke test suite and reopen platform to all clinics | QA Lead / Release Manager |

Communication plan

- Internal Escalation: Release Manager notifies Executive Team and incident response bridge via Slack/Paging within 5 minutes.
- External Communication: Support Lead updates status.nexacare.com and dispatches priority advisory to all 300+ clinics: 'The scheduled platform update has been postponed for further optimization. Stable platform v2.x remains fully available.'

Estimated rollback time

Total Rollback Duration: 60 - 90 minutes maximum. Executing by 04:30 AM guarantees full v2.x system restoration and verification before the 06:00 AM EST clinic opening deadline.

Data migration plan

Systems involved

- Source system: NexaCare Legacy Production Database (PostgreSQL 12 - Monolithic v2 Schema)

- Destination system: NexaCare v3.0 Partitioned Database (PostgreSQL 15 - Normalized Microservice Schema)

Field mapping

| Source Field | Destination Field | Transformation / Logic |
| --- | --- | --- |
| patient_id (INT) | patient_uuid (UUID) | Deterministic UUIDv5 generation based on legacy ID namespace. |
| phone_home, phone_mobile | mobile_number_e164 (VARCHAR) | Normalize and convert phone numbers to ITU E.164 standard (+1XXXXXXXXXX). |
| sms_consent (0/1/NULL) | sms_opt_in_status (ENUM) | Map 1 -> OPTED_IN, 0 -> OPTED_OUT, NULL -> PENDING_CONFIRMATION. |
| first_name, last_name | legal_name_encrypted (BYTEA) | Sanitize and encrypt using AES-256-GCM envelope encryption (HIPAA PHI). |
| N/A (New Feature) | calendar_sync_provider | Initialize as 'NONE'; updated dynamically upon Google/Outlook OAuth link. |
| N/A (New Feature) | availability_version (INT) | Initialize default to 1 for optimistic concurrency locking control. |

Migration volume

Total Record Volume: 1,200,000 Patient Records, 8,540,000 Historical Appointments, 312 Clinic Profiles.
Batch Strategy: Script executes in controlled transactional chunks of 10,000 records with progress tracking, automated commit checkpoints, and dedicated exception routing to avoid database table locking.

Validation steps

- Pre-migration sanity checks

- Migration logs review

- Post-migration field and count verification

- Exception reporting and remediation plan

Post-deployment monitoring summary

Key metrics to monitor

| Metric | Threshold / SLA | Monitoring Tool / Method |
| --- | --- | --- |
| Platform Uptime / Availability | >= 99.9% uptime (<= 43.8 min/month) | Synthetic Probes (Pingdom / Better Uptime) |
| HTTP 5xx Server Error Rate | < 0.1% of total requests (Alert if > 0.5%) | Datadog APM / Application Load Balancer |
| Booking Transaction Latency (P95) | < 500 ms (Alert if > 1,500 ms) | Datadog APM Distributed Tracing |
| SMS Reminder Delivery Latency | < 2 minutes from schedule (Alert if > 5 min) | Third-Party Webhook Delivery Logs |
| SMS Delivery Failure Rate | < 1.0% failure (Alert if > 3.0%) | Logstash / Elasticsearch Aggregation |
| Doctor Availability Update Sync | < 5.0 seconds cross-session propagation | WebSocket Gateway Telemetry / Prometheus |
| Calendar Sync Authorization Errors | < 0.5% failure rate (Alert if > 2.0%) | Application Exception Logs (Sentry / ELK) |

Monitoring responsibilities

| Team / Person | Monitoring Role | Frequency / Schedule |
| --- | --- | --- |
| DevOps / SRE Team | Infrastructure health, container autoscaling, CPU/RAM, DB connection pool | Continuous 24/7 (Hypercare War Room) |
| Database Administrator (DBA) | Database lock contention, slow query logs, read replica replication lag | Every 30 minutes in peak hours |
| QA & Automation Lead | Synthetic user transaction testing, smoke test validation | Hourly automated test execution |
| Customer Support Lead | Pilot clinic tickets, feedback triage, incident escalation to engineering | Continuous shift monitoring |
| Systems Analyst / Architect | Overall health KPIs, executive status reports, capacity alignment | Daily 08:00 AM & 05:00 PM reviews |

Response plan

- Severity 1 (Critical - P0): Automated PagerDuty escalation calls SRE, DevOps, and Lead Architect immediately. War Room convenes within 10 minutes. If core booking is impaired, circuit breaking activates.
- Severity 2 (Major - P1): Slack alert to #eng-triage; assigned engineer investigates within 30 minutes.
- Severity 3 (Minor - P2): Ticket logged automatically in Jira backlog for scheduled sprint remediation.

## Feature 2: Real-Time Doctor Availability & Concurrency Control

Test Objective: Verify instant multi-session availability updates, accurate slot locking, and zero double-bookings under high concurrency and network drops.

Preconditions: Doctor D schedule active in Clinic Portal; 2 authenticated patient accounts active on web portal; WebSocket gateway online.

| Step / TC ID | Test Action | Expected Result | Risks / Edge Cases / Notes |
| --- | --- | --- | --- |
| TC-AVAIL-01.1 | Doctor alters schedule slot (opens/blocks slot S1) in Clinic Web Portal. | WebSocket server broadcasts availability delta payload to all connected clients; slot color changes within <= 5s. | Risk: High broadcast fanout overhead if hundreds of patients are connected simultaneously. |
| TC-AVAIL-02.1 | Simulate 2 patients (User A and User B) simultaneously clicking 'Confirm Booking' on identical slot S1 at t=0ms (Race Condition). | Database transactional lock (pessimistic lock) grants commit to User A; User B receives HTTP 409 Conflict with clear modal notice. Zero double-booking. | Risk: Ghost bookings or double allocations under high Monday morning concurrency. Requires strict row-level isolation. |
| TC-AVAIL-03.1 | Patient browser experiences spotty clinic Wi-Fi (WebSocket drops); patient attempts to book an expired slot. | Client automatically detects socket disconnect, fails pre-booking validation, and forces background availability refresh. | Edge Case: Pilot clinics with poor network infrastructure seeing stale availability data on desktop screens. |

## Feature 3: Bi-Directional Calendar Integration (Google Calendar & Microsoft Outlook)

Test Objective: Validate seamless event creation, updates, and cancellations across Google Calendar and Microsoft Outlook, including OAuth lifecycle and timezone parity.

Preconditions: User linked active Google/Outlook account; OAuth refresh token encrypted in database; mock external calendar endpoints ready.

| Step / TC ID | Test Action | Expected Result | Risks / Edge Cases / Notes |
| --- | --- | --- | --- |
| TC-CAL-01.1 | Patient authenticates Google/Outlook account via OAuth 2.0 and books an appointment in NexaCare. | Appointment event created in external calendar within <= 15s with clinic address, date, time, and clinic name. | Risk: OAuth token scope leakage or excessive permissions. Must strictly request calendar.events scope. |
| TC-CAL-02.1 | Patient reschedules or cancels appointment inside NexaCare web platform. | Webhook triggers external calendar update; existing calendar entry is modified or deleted cleanly without orphan events. | Risk: Desynchronization if external API is temporarily down; requires persistent retry queue with exponential backoff. |
| TC-CAL-03.1 | Patient revokes NexaCare access token from Google Account security settings prior to sync update. | NexaCare receives HTTP 401/403, updates sync_status to 'ACTION_REQUIRED', and alerts user via UI banner without failing booking. | Edge Case: Expired/revoked OAuth refresh tokens causing silent booking errors in clinic schedules. |
| TC-CAL-04.1 | Clinic in EST (UTC-5) schedules appointment for patient traveling in PST (UTC-8). | Event stored internally in UTC ISO-8601; external invitation renders at exact matching local time for both parties. | Edge Case: Daylight saving transitions or cross-timezone appointment misalignments leading to missed doctor visits. |

## Feature 4: Redesigned User Interface (Responsive Design & WCAG 2.1 AA Accessibility)

Test Objective: Ensure complete responsive usability across mobile, tablet, and desktop devices, alongside strict WCAG 2.1 AA accessibility compliance.

Preconditions: Staging frontend deployed with redesigned CSS/JS design system; screen reader tools (NVDA/JAWS) and mobile emulators configured.

| Step / TC ID | Test Action | Expected Result | Risks / Edge Cases / Notes |
| --- | --- | --- | --- |
| TC-UI-01.1 | Execute full booking journey on viewport width 375px (iPhone/Android mobile screen). | Responsive layout renders without horizontal scroll; touch targets >= 48x48px; booking completed in <= 3 steps. | Risk: Overflow of schedule slot tables on smaller smartphone displays causing booking drop-offs. |
| TC-UI-02.1 | Execute booking journey on viewport width 1440px (Desktop clinic reception workstation). | Full calendar grid renders clearly; multi-provider view displays without layout overlap or rendering artifacts. | Risk: Desktop performance stuttering when rendering dozens of provider schedules simultaneously. |
| TC-UI-03.1 | Navigate entire booking workflow using keyboard-only navigation (Tab, Enter, Space, Arrow keys). | Visible focus indicators present on 100% interactive elements; modal trap focus works correctly; zero keyboard traps. | Compliance: WCAG 2.1 AA requirement. Failure excludes users with motor impairments. |
| TC-UI-04.1 | Audit interface with NVDA and JAWS screen readers across appointment selection and confirmation dialogs. | All interactive controls have descriptive aria-labels; dynamic availability updates announced via aria-live regions. | Compliance: Accessibility compliance mandatory for healthcare platforms serving diverse demographics. |

## Feature 5: Clinic PMS/API Integration & Pilot Clinic Hybrid Workflows

Test Objective: Verify backward compatibility for external clinic patient management systems (PMS) and validate hybrid API/UI workflows across the 20 pilot clinics.

Preconditions: API Gateway running with v2 backward-compatibility middleware; test clinic registered in Pilot program with active API keys.

| Step / TC ID | Test Action | Expected Result | Risks / Edge Cases / Notes |
| --- | --- | --- | --- |
| TC-API-01.1 | Clinic PMS sends REST API request to POST /api/v2/appointments using legacy payload format. | API Gateway accepts request; backward-compatibility adapter maps legacy fields to v3.0 schema; returns HTTP 201 Created. | Risk: Breaking external clinic EHR/PMS integrations that rely on v2 JSON schema contracts. |
| TC-API-02.1 | Clinic PMS queries GET /api/v2/doctors/{id}/availability for real-time schedule. | API responds within <= 250ms with standardized ISO-8601 availability payload matching exact legacy format. | Risk: API latency causing timeouts in third-party clinic electronic health record software. |
| TC-PILOT-01.1 | Pilot Clinic #4 creates appointment via EHR API integration; receptionist verifies live update on NexaCare Web Portal. | Appointment immediately reflects on Web UI in real-time (< 3s); SMS reminder scheduled; calendar invite dispatched. | Pilot Focus: Validates hybrid clinic environment where staff use both local PMS software and web platform simultaneously. |